## Sheet1
Project | Delmart
Srake Holders / Customers / Users | Delmart co.
Created By | Sala Uddin
Epic | User Story ID | Feature/Title | User Story | Status | Story Point | Sprint
For a new e-commerce website to launch ,the highest business value will be when a new user is able to buy an item from the website. Amazon_Epic_001 | US001 | First-time visitor can make the payment as a guest user without having to register | As a first-time visitor to the e-commerce website I want to be able to buy a listed product so that I can use the product I buy | New | 8 | 1
| US002 | new user can register on the website | As a first-time visitor to the website, I want to be able to register on the website , so that I can browse and buy listed products from the website | New | 3 | 2
| US003 | registered users can browse item listed | As a registred website user , I want to be able to browse listed products from the website , so that I can make my choice and buy a listed product from the website | New | 5 | 2
| US004 | registered user can add items to the cart | As a registred website user , I want to be able to add items to the cart, so that I can buy a listed product from the website | New | 5 | 3
| US005 | registered user can make payments for the items added to the cart | As a registred website user, I want to be able to buy listed products , so that I can use the product I buy. | New | 8 | 3